ULP Development Sequencing

Phased Delivery Plan: Multi-Region (India + US) Edition

Version 2.0

May 2026 (supersedes v1.0)

Confidential — for ULP Engineering and Project Management

# Change Log

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | 2026-04-30 | Shankar | Initial release. India-only sequencing across 27 modules. |
| 2.0 | 2026-05-XX | Shankar | MAJOR: Refactored for multi-region. Added US client 6-milestone alignment. Restructured phases to deliver country-agnostic core first, then country plugins in parallel. Total duration extended from 7 months to 9 months to accommodate dual compliance. |

# 1. Executive Summary

## 1.1 What this document does

This document defines the phased build plan for the Unified Logistics Platform v2.0. It serves three audiences:

- Engineering: which modules are built when, with which dependencies

- Indian client: how their original India-focused requirements get delivered

- US client: how their 6-milestone proposal maps to ULP modules and timeline

## 1.2 Top-line plan

| Metric | Value |
| --- | --- |
| Total duration | 9 months from kickoff |
| Number of phases | 5 |
| Total modules | 27 (15 core + 8 with country plugins + 4 country-specific) |
| Engineering team size | 6 backend + 3 frontend + 1 mobile + 1 AI/ML + 1 DevOps + 1 QA = 12 people |
| Total engineering effort | ~108 person-months |
| Demo cadence | Every 2 weeks |
| Client review cadence | End of each phase |

## 1.3 Key strategic decisions

- Build country-agnostic core FIRST (Phases 1-2). This unblocks both India and US tracks.

- Run India-specific (Phase 3a) and US-specific (Phase 3b) compliance work IN PARALLEL after core stabilizes.

- Phase 4 = Dashboards + AI integration + UX polish across both regions simultaneously.

- Phase 5 = Hardening, performance, security audit, go-live readiness.

- Both clients see continuous delivery; neither feels deprioritized.

# 2. Phase Overview

| Phase | Months | Theme | Modules touched | Output |
| --- | --- | --- | --- | --- |
| Phase 1 | 1-2 | Foundation | M1, M21, M26, M27, M3, infra | Tenant onboarding works; users can sign in; basic data entry |
| Phase 2 | 3-4 | Operations Core | M5, M8, M13-Core, M14, M17-Core | End-to-end shipment + warehouse + transport workflow (no country compliance yet) |
| Phase 3a | 5-6 | India Compliance | M4-IN, M13-IN, M17-IN, M15, M18, M19, M20 | Indian tenants can file BOE/SB/EWB/IRN/GSTR. Indian client gets full v1 functionality. |
| Phase 3b | 5-6 (parallel) | US Compliance | M4-US, M13-US, M17-US, M15-US, M18-US, M19-US | US tenants can file CBP entries, AES, sales tax, 1099. US client gets full v1 functionality. |
| Phase 4 | 7-8 | Visibility + AI + Polish | M24, M28, frontend polish, M2, M6, M16, M22, M23 | Dashboards, Control Tower, AI features, all secondary modules |
| Phase 5 | 9 | Harden + Launch | All modules | Performance tuning, security audit, prod readiness, go-live |

# 3. Client Milestone Alignment

## 3.1 US client 6-milestone proposal alignment

The US client proposal defines 6 milestones. Below shows how each maps to ULP phases and modules:

### 3.1.1 Milestone 1 (US client) — Control Tower + Order/Doc/Profiles

Client expectation: Control Tower, shipment views (Ocean/Air Import/Export), filters, order management, document generation (AN, DO, B/L, Letter of Guarantee, ATM, ITN, US Customs Hold), profiles & POA tracking.

| Client feature | ULP module | Phase delivered |
| --- | --- | --- |
| Control Tower | M24 Dashboards | Phase 4 (months 7-8) |
| Shipment views (Ocean/Air Import/Export) | M5 Freight Forwarding | Phase 2 + Phase 4 polish |
| Filters (MBL/HBL/Cntr/POL/POD) | M5 + M4 search APIs | Phase 2 |
| Watchlist / Reminders / Holds | M27 Notifications + M24 widgets | Phase 1 (notifications) + Phase 4 (UI) |
| Chat box | M27 Notifications (in-app) | Phase 4 |
| Order management — Leads (3PL only) | M2 Sales/CRM | Phase 4 |
| Quote template (freight, brokerage, trucking, warehousing) | M14 Pricing & Quotation | Phase 2 |
| ERP for Vendor Account | M1 Master Data + M3 Vendor | Phase 1 |
| Generate New Shipment (MBL/HBL) | M5 Freight Forwarding | Phase 2 |
| Generate Documents (AN, DO, RI, Letter of Guarantee) | M6 Doc Generation + M4-US plugin | Phase 3b |
| ATM, ITN, US Customs Hold/Exam Notice | M4-US CBP/ABI plugin | Phase 3b |
| Bill of Lading w/ surrender, telex release, original stamps | M5 + M6 (custom templates) | Phase 3b |
| Document Management (shipping docs / invoices separated) | M21 Document Management | Phase 1 |
| Memo Notes (internal) | M27 Notifications (notes) | Phase 4 |
| Profiles & Settings, login by email | M26 RBAC | Phase 1 |
| POA tracking (expiration) | M1 Master Data (compliance master) | Phase 1 |
| Permits (company, commodity) with expiration | M1 Master Data | Phase 1 |

Milestone 1 readiness: End of Phase 4 (Month 8). Earlier preview available end of Phase 2 (Month 4) for non-customs features.

### 3.1.2 Milestone 2 — RFQ, PO, Active Shipments, US 7501, PGA holds

| Client feature | ULP module | Phase |
| --- | --- | --- |
| RFQ (3PL) | M2 + M14 | Phase 4 |
| Purchase Orders + approval workflow | M7 Procurement | Phase 4 |
| Active Shipments (Bookings) | M5 Freight Forwarding | Phase 2 |
| Active Shipments (In-Transit) | M5 + M13 | Phase 2 |
| Vessel Departure → Arrival → Discharged → Gate Out → Empty Return | M5 (events) + M13 (status) | Phase 2 |
| Demurrage / Per Diem tracking | M5 + M14 | Phase 4 |
| Customs info, duty per product on 7501 | M4-US CBP plugin | Phase 3b |
| PGA holds (FDA, USDA, EPA) | M4-US CBP plugin | Phase 3b |
| Warehouse status integration (FDA holds) | M4-US + M8 WMS | Phase 3b |

### 3.1.3 Milestone 3 — Accounting (full)

| Client feature | ULP module | Phase |
| --- | --- | --- |
| Invoice approval workflow + drafts | M17-Core | Phase 2 |
| AR/AP linkage | M17-Core | Phase 2 |
| Credit card payments + receipt photo upload | M17 + M21 | Phase 4 |
| General Expense (fixed + variable) | M17-Core | Phase 2 |
| Settlement (AR + AP) + reverse | M16 Settlement | Phase 4 |
| Deposit / reverse | M16 | Phase 4 |
| Print Multiple Checks | M17-US bank module | Phase 3b |
| Aging report (multi-axis: invoice/ETD/ETA/Final ETA/Due Date) | M17 + M24 | Phase 4 |
| Invoice history + charge details | M17 | Phase 2 |
| Payment history inquiry (multi-filter) | M17 + M24 search | Phase 4 |
| A/R A/P report + Income/Expense | M17 + M24 | Phase 4 |
| Comparative profit by year | M24 | Phase 4 |
| Past Due Notices | M17 dunning + M27 | Phase 4 |
| Customer Statements | M17-US-Plugin | Phase 3b |
| Bank reconciliation, monthly statement, GL, Trial Balance, BS, P&L | M17-Core + M17-US (GAAP) | Phase 2 (Core) + Phase 3b (US-specific) |
| Email connection setup, custom templates | M27 Notifications | Phase 1 |
| Automatic notifications (holds 7 days, statements, arrivals, container returns) | M27 + M24 | Phase 4 |

### 3.1.4 Milestone 4 — Trucking

| Client feature | ULP module | Phase |
| --- | --- | --- |
| Trucking ops (orders, dispatch, equipment) | M13 Transportation Core | Phase 2 |
| Driver / chassis / truck masters + maintenance | M1 + M13 | Phase 1 + Phase 2 |
| Workflow: New Order → Dispatched → Outgated → Completed | M13 | Phase 2 |
| Calendar dispatch (drag-drop driver/chassis) | M13 frontend | Phase 4 |
| Driver app (status / location / POD upload) | M13 mobile (KMP) | Phase 2 (basic) + Phase 4 (polish) |
| Accessorial fees mid-workflow | M13 + M14 | Phase 4 |
| ELD integration, HOS, IFTA (US) | M13-US plugin | Phase 3b |

### 3.1.5 Milestone 5 — Warehousing

| Client feature | ULP module | Phase |
| --- | --- | --- |
| Inventory tracking (unit, case, pallet) | M8 WMS | Phase 2 |
| Bin / rack / stock transfer | M8 WMS | Phase 2 |
| Product catalog with images, weights, dimensions | M1 Master Data + M21 | Phase 1 |
| Barcode generation per pallet | M8 + M21 | Phase 2 |
| SKU costing (landed cost + warehousing cost) | M8 + M17 | Phase 4 |
| Pick list with assignment | M8 | Phase 2 |
| Cycle count | M8 | Phase 4 |
| Expiration warnings (6 months) | M8 | Phase 4 |
| Auto storage billing (weekly/biweekly/monthly, cbm/pallet) | M8 + M14 + M16 | Phase 4 |
| Sales Order with availability + in-transit + at-origin | M5 + M8 | Phase 2 |
| B/L generation | M5 + M6 | Phase 2 |
| Warehouse barcode scanner app | M8 mobile (KMP) | Phase 4 |
| Documents: PO/PI, POD, GRN, Shipping Order, B/L | M21 + M8 | Phase 2 |
| Blank Master/House template (services not tied to shipment) | M5 + M6 | Phase 4 |

### 3.1.6 Milestone 6 — Doc Functions + Reports

| Client feature | ULP module | Phase |
| --- | --- | --- |
| Text overlay on documents at print | M6 Doc Generation | Phase 4 |
| Stamps / signatures | M6 + M21 | Phase 4 |
| Reports for shippers/cnees (top suppliers, countries, ports, SKUs) | M24 Dashboards | Phase 4 |
| SKU-level inventory location reports (origin, in-transit, destination) | M8 + M5 + M24 | Phase 4 |
| Vendor reports (TEU volume change, top performers, inactivity) | M24 | Phase 4 |
| Profit reports (by agent, salesperson, customer, shipper, consignee) | M17 + M24 | Phase 4 |
| Workload report by user | M26 + M24 | Phase 4 |
| Shipment tracking reports (country, POL, POD, carrier, move type) | M5 + M24 | Phase 4 |

# 4. Indian Client Alignment

The Indian client engaged before the US client. Their expectations were fully captured in v1.0 documents and remain unchanged in v2.0. The multi-region refactor does not delay or compromise Indian deliverables.

## 4.1 Phase-by-phase Indian client value

| Phase | Indian-client visible delivery |
| --- | --- |
| Phase 1 (M1-2) | Tenant signup, login, master data CRUD, document upload |
| Phase 2 (M3-4) | Shipment booking, MBL/HBL, warehouse GRN+putaway, trip planning, GL/AR/AP/period close primitives, basic pricing |
| Phase 3a (M5-6) | BOE/SB filing via ICEGATE, EWB generation, IRN generation, SCMTR Arrival/Departure manifests, GSTR-1/3B preview, TDS computation |
| Phase 4 (M7-8) | Control Tower (re-skinned for India), AI document extraction, dashboards, RFQ workflows |
| Phase 5 (M9) | Production rollout, security audit, performance hardening |

Indian client gets parity with v1 plan plus benefits of multi-region architecture (cleaner separation of compliance from core, easier upgrades, future regional expansion).

# 5. Detailed Phase Plan

## 5.1 Phase 1: Foundation (Months 1-2)

### 5.1.1 Goal

Establish the platform skeleton. Tenants can sign up, users can sign in, master data can be entered, documents can be uploaded.

### 5.1.2 Deliverables

| Module | Scope |
| --- | --- |
| Infrastructure | Docker Compose MVP stack ready; Terraform for India + US dev; CI/CD pipelines |
| M1 Master Data | Customer, vendor, product, port, currency masters (with country_code) |
| M21 Doc Management | Upload, retrieval, OCR, versioning |
| M26 RBAC | Roles, permissions, MFA, JWT issuance with country_code claim |
| M27 Notifications | Email/SMS/WhatsApp via abstractions; MailHog/MSG91 for MVP |
| M3 Vendor Management | Vendor onboarding, performance tracking |
| Internationalization runtime | Currency service, time zone service, locale service, plugin loader |

### 5.1.3 Phase 1 acceptance criteria

- A new tenant can sign up choosing IN or US country

- Users can be invited and authenticate via Azure AD B2C / Keycloak

- Master data CRUD works with proper validation per country

- Document upload + retrieval works with WORM compliance

- Email/SMS notifications dispatch successfully

- Compliance plugin DI resolution works for both IN and US tenants

## 5.2 Phase 2: Operations Core (Months 3-4)

### 5.2.1 Goal

Build the country-agnostic operational backbone: shipments, warehousing, transportation, accounting primitives, pricing.

### 5.2.2 Deliverables

| Module | Scope |
| --- | --- |
| M5 Freight Forwarding | Shipment lifecycle, MBL/HBL, manifest tracking, multi-modal |
| M8 WMS | GRN, putaway, picking, bin management, cycle count |
| M13 Transportation Core | Trip lifecycle, driver/vehicle management, GPS ingestion, geofencing, POD |
| M14 Pricing | Rate cards, quote generation, accessorials |
| M17 Accounts Core | GL, chart of accounts, journals, AR, AP, period close primitives, multi-currency |
| M6 Doc Generation | Template engine; common doc templates (universal, no country-specific) |

### 5.2.3 Phase 2 acceptance criteria

- End-to-end demo: customer creates shipment → vendor warehousing → trucking → invoicing

- All amounts properly handled in multi-currency with FX revaluation

- Trip GPS data flowing from driver app + telematics into MySQL

- Period close primitives working (open → close → can't modify)

- Indian client and US client can both demo this with their own data

## 5.3 Phase 3a: India Compliance Plugins (Months 5-6)

### 5.3.1 Goal

Add complete India compliance: customs filing, GST, EWB, TDS, GSTR. Indian client receives full v1.0 functionality.

### 5.3.2 Deliverables

| Module | Scope |
| --- | --- |
| M4-IN CHA Plugin | BOE filing, SB filing, IGM/EGM tracking, AEO compliance, Indian customs duty calc (CIF method) |
| M13-IN Transport Plugin | e-Way Bill (Part A + Part B), validity, extension, cancellation, NIC API integration |
| M17-IN Accounts Plugin | GST (CGST/SGST/IGST), IRN generation, IRP integration, TDS computation, GSTR-1/3B/9 returns, Form 16A |
| M15 DGFT Schemes | EPCG, RoDTEP, Advance Authorization, EODC, scheme stacking |
| M18 GST Returns | GSTR-1, GSTR-3B, GSTR-9, GSTR-9C reconciliation |
| M19 TDS/TCS | TDS computation, deposit, returns, certificates |
| M20 SCMTR | Sea Cargo Manifest, PCIN/MCIN/CSN, ICEGATE MFTP, stuffing/stripping |

### 5.3.3 Phase 3a acceptance criteria

- A live BOE can be filed via ICEGATE sandbox

- IRN generated for invoice via NIC IRP sandbox

- e-Way Bill generated and validated via NIC EWB sandbox

- GSTR-1 preview matches sales register

- Indian client signs off as v1-equivalent

## 5.4 Phase 3b: US Compliance Plugins (Months 5-6, PARALLEL with 3a)

### 5.4.1 Goal

Add complete US compliance: CBP/ABI filing, AES, sales tax, 1099. US client receives v1.0-equivalent functionality.

### 5.4.2 Deliverables

| Module | Scope |
| --- | --- |
| M4-US CHA Plugin | CBP ABI filing (entry types: SE, SO), Form 7501, ATM, ITN, AES export, ISF (10+2), PGA integrations (FDA, USDA, EPA) |
| M13-US Transport Plugin | DOT compliance, ELD integration, HOS rules, IFTA fuel tax tracking |
| M17-US Accounts Plugin | US sales tax (state nexus, marketplace facilitator), 1099-NEC/MISC/K, W-9, GAAP period close, US bank reconciliation |
| M15-US Trade Programs | C-TPAT, FAST, Trusted Trader (placeholder) |
| M18-US Sales Tax Returns | Multi-state filing via Avalara/TaxJar integration |
| M19-US 1099 Reporting | Annual 1099 generation, e-file via service provider |
| US Document Library | AN (rated/non-rated), DO, RI, Letter of Guarantee, Authority to Make Entry, Turnover/Release Order, I.T., US Customs Hold/Exam Notice, B/L variants |

### 5.4.3 Phase 3b acceptance criteria

- A live CBP entry can be filed via ABI sandbox

- Form 7501 PDF generates with correct duty calculation

- AES export filing works

- PGA hold (FDA) workflow demonstrable

- Multi-state sales tax works for CA + NY + TX (3-state nexus test)

- 1099-NEC generates correctly for sample vendors

- US client signs off as v1-equivalent

## 5.5 Phase 4: Visibility, AI, Polish (Months 7-8)

### 5.5.1 Goal

Add Control Tower, dashboards, AI-augmented workflows, secondary modules, and UX polish across both regions.

### 5.5.2 Deliverables

| Module | Scope |
| --- | --- |
| M24 Dashboards / Control Tower | Executive, operations, finance dashboards; Control Tower (shipper/cnee visibility); 60+ widgets |
| M28 AI Services | FastAPI/LangGraph agents; document extraction (BOE, invoices, BL); RAG-based compliance Q&A |
| M2 Sales / CRM | Lead, opportunity, RFQ workflows |
| M16 Settlement | AR/AP settlement, reverse, deposit, dunning |
| M22 Quality | Inspections, NCR (relevant for warehousing) |
| M23 HR / Payroll | Driver/warehouse staff onboarding, attendance (per-country payroll plugins) |
| Frontend polish | Mobile responsive, accessibility (WCAG 2.1), i18n cleanup |
| Driver app v2 | Battery management, offline POD, route guidance |
| Reports | All client-requested reports (Milestone 6 of US client proposal) |

### 5.5.3 Phase 4 acceptance criteria

- Control Tower visible to shipper/cnee tenants with all required filters

- All MS6 reports working for both regions

- AI document extraction demoed for BOE (India) and 7501 (US)

- Customer demos pass UX review

## 5.6 Phase 5: Hardening + Launch (Month 9)

### 5.6.1 Goal

Production readiness. Performance tuning. Security audit. Documentation. Go-live.

### 5.6.2 Activities

- Load testing (5,000 concurrent users per region)

- Security audit (external penetration test + remediation)

- SOC 2 Type II readiness (US region)

- DPDP Act compliance audit (India region)

- Performance tuning (DB indexes, cache hit rates, slow queries)

- Disaster recovery drill (failover and recovery test)

- User documentation, video tutorials, in-app onboarding

- Migration from MVP local stack to Azure production for early-access customers

- Go-live cutover plan

# 6. Module Dependencies

## 6.1 Critical path

Modules in the critical path determine the minimum project duration. Delays here delay everything:

- M1 Master Data (Phase 1) → blocks every other module

- M26 RBAC (Phase 1) → blocks every API

- M5 Freight Forwarding (Phase 2) → blocks M4 (CHA), M14 (pricing on shipments), M24 (dashboards)

- M17 Accounts Core (Phase 2) → blocks M16 (settlement), M17-IN/M17-US plugins

- M4-IN / M4-US (Phase 3a/3b) → blocks compliance dashboards in M24

## 6.2 Parallelization opportunities

- Phase 1: M1, M21, M26, M27 can be built in parallel by 4 separate streams

- Phase 2: M5, M8, M13-Core, M17-Core, M14 can largely parallelize after M1 stable

- Phase 3a + 3b: India team and US team work IN PARALLEL (different developers, same codebase)

- Phase 4: Many secondary modules parallelize (M2, M22, M23 don't cross-dependent)

## 6.3 Module dependency graph (simplified)

Phase 1                    Phase 2                Phase 3a (IN)        Phase 3b (US)       Phase 4         Phase 5

========                   ========               =============        =============       =========       ========

M1 Master Data ─────┬─── M5 Forwarding ─────┬─── M4-IN CHA ─────────┬── M4-US CHA ────────┬── M24 ─────┬── Hardening

│                       │                       │                     │            │

M26 RBAC ───────────┼─── M14 Pricing ───────┼─── M13-IN EWB ────────┼── M13-US ELD ───────┼── M28 AI ──┘

│                       │                       │                     │

M21 DocMgmt ────────┼─── M8 WMS ────────────┼─── M17-IN GST/TDS ────┼── M17-US Tax/1099 ──┼── M2/M16/M22/M23

│                       │                       │                     │

M27 Notif ──────────┼─── M13-Core ──────────┼─── M15/M18/M19/M20 ───┼── M15-US/M18-US ────┘

│

M3 Vendor ──────────┴─── M17-Core

M6 Doc Gen ──────────────────────────────── (used throughout)

# 7. Team Allocation

## 7.1 Recommended team structure

| Role | Headcount | Phase 1 | Phase 2 | Phase 3a (IN) | Phase 3b (US) | Phase 4 | Phase 5 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Backend (.NET) | 6 | All on core | Module owners | 3 on India | 3 on US | Polish + AI | Hardening |
| Frontend (Angular) | 3 | Auth + master data UI | Operations UI | India compliance UI | US compliance UI | Dashboards + UX | Bug fix |
| Mobile (KMP) | 1 | Driver app skeleton | GPS + POD | India variants | US variants | Polish | Bug fix |
| AI / ML | 1 | Setup | RAG infrastructure | India doc extraction | US doc extraction | Agents + Control Tower | Tune |
| DevOps | 1 | IaC + CI/CD | Per-module pipelines | IN region prod | US region prod | Observability | Audit |
| QA | 1 | Test framework | Module testing | IN compliance tests | US compliance tests | E2E + perf | UAT |

## 7.2 Specialized SMEs (consultants, project basis)

- Indian customs SME (CHA license holder) — Phase 3a, ~2 person-months

- US customs broker SME — Phase 3b, ~3 person-months

- Indian CA / accountant — Phase 3a, ~1 person-month

- US CPA — Phase 3b, ~2 person-months

- Security auditor — Phase 5, ~3 weeks

# 8. Risk Management

| Risk | Mitigation |
| --- | --- |
| CBP ABI integration takes longer than 2 months due to certification | Engage CBP-certified consultant in Phase 1; start sandbox testing early in Phase 2; have fallback to manual filing UI for first month of go-live |
| Indian client objects to parallel US development | Communicate that India work is on track; share Phase 3a milestones; offer dedicated India sub-team if needed |
| US client expects features Indian client doesn't care about (Control Tower) | Build Control Tower in M24 as country-agnostic feature; demo to both clients; let Indian client opt-in |
| Feature drift during Phase 3 between IN and US plugins | Mandatory weekly cross-team sync; shared Internationalization Guide as source of truth; refactor reviews on every PR touching plugin interfaces |
| Performance degrades when running both plugin sets | Plugins lazy-loaded; only one country active per tenant; perf testing in Phase 5 |
| SOC 2 audit reveals issues delaying US go-live | Engage auditor in Phase 4 to do gap assessment; remediate during Phase 5 |
| Multi-region deployment costs more than budgeted | Use Azure Reserved Instances; right-size based on actual telemetry from Phase 4 |
| Engineering attrition during 9-month project | Cross-training mandatory; documentation gates per phase; have a buffer of 1-2 contractors on standby |

# 9. Milestones and Demo Schedule

## 9.1 Major milestones

| Date | Milestone | Audience |
| --- | --- | --- |
| End Month 2 | Foundation demo: signup, login, master data | Both clients + leadership |
| End Month 4 | Operations demo: end-to-end shipment + warehouse + transport (no compliance) | Both clients |
| End Month 6 | India compliance demo (Phase 3a complete) | Indian client + leadership |
| End Month 6 | US compliance demo (Phase 3b complete) | US client + leadership |
| End Month 8 | Control Tower demo + reports + AI features | Both clients + leadership |
| End Month 9 | Production go-live | Customers |

## 9.2 Bi-weekly demo cadence

Every two weeks, the team demos progress to internal stakeholders. Every other demo (monthly) is also shared with clients.

## 9.3 Phase gates

Each phase has a formal gate review before the next phase starts:

- Acceptance criteria signed off (engineering lead + product owner + client where relevant)

- Documentation updated (LLDs, API specs, runbooks)

- Test coverage targets met (>80% on new code)

- Security review completed (SAST/DAST clean)

- Demo recorded and archived

# 10. Communication Plan

## 10.1 Internal

- Daily standup: engineering team

- Weekly syncs: tech lead + product owner

- Bi-weekly: full team retro + planning

- Monthly: leadership review (status, risks, decisions)

## 10.2 Indian client

- Bi-weekly: progress update + demo (in IST)

- End of phase: formal sign-off review

- Compliance committee review at end of Phase 3a

## 10.3 US client

- Bi-weekly: progress update + demo (in ET)

- End of phase: formal sign-off review

- Compliance committee review at end of Phase 3b

## 10.4 Joint sessions

- End of Month 4: joint demo (Operations Core - country-agnostic)

- End of Month 8: joint demo (Control Tower + AI)

- Monthly: joint architecture review (technology decisions affecting both)

— End of Development Sequencing v2.0 —

Cross-references:

- ULP_Rework_MasterPlan_v1.0.docx — full rework roadmap

- ULP_Internationalization_Guide_v1.0.docx — multi-region foundation

- ULP_HLD_v2.0_MultiRegion.docx — high-level design

- ULP_LLD_M*_v2.0_*.docx — module-level designs (in rework)

- ULP_DevelopmentGuide_v1.0.docx — engineering practices