ULP Rework Master Plan

Multi-Region Refactor for India + United States Markets

Version 1.0

Compiled: May 2026

Confidential — for ULP Project Team and Client Stakeholders

# 1. Executive Summary

The Unified Logistics Platform (ULP) was originally designed for the Indian logistics market with deep integration into Indian compliance systems (ICEGATE, GST IRP, e-Way Bill, DGFT, SCMTR). A new United States client engagement requires the platform to support US freight forwarding workflows including CBP/ABI customs filing, US GAAP accounting, and a freight-forwarder-style "Control Tower" user experience.

This Master Plan details the rework required to convert ULP from an India-only product to a multi-region platform serving India + United States as the first two markets, with an extension pattern for future regions (UAE, EU, Southeast Asia).

### 1.1 Key numbers

| Metric | Value |
| --- | --- |
| Existing documents | 18 |
| Documents requiring rework | 13 (72%) |
| Documents needing minor touch-up | 5 (28%) |
| New documents to create | 3 |
| Total documents at end of rework | 21 |
| Total existing pages affected | ~210 of ~700 (30%) |
| New pages to write | ~85 |
| Total writing effort | ~225 hours |
| Foundation tier (must-do-first) | 4 documents, ~58 hours |
| Calendar at full-time pace | ~6 weeks |
| Calendar at evening pace | ~14 weeks |
| Calendar with Claude assistance | ~18-20 focused sessions |

### 1.2 Deviation from US client expectation

Per analysis of the client proposal (six-milestone scope):

- Strong direct match: ~30% of ULP modules already cover client requirements

- Partial match needing adaptation: ~25% of modules

- Net-new work for US compliance: ~12% (US CBP, PGA holds, US accounting variants)

- Indian-specific work irrelevant for US client: ~33% (parked, not deleted; remains for India market)

Net effort to satisfy this client: ~45-50% of original ULP build estimate.

# 2. Strategic Approach

## 2.1 Refactor, do not fork

The chosen strategy is to refactor existing documents to be multi-region-aware, with India + United States as the first two locales and a clear pattern for adding future regions. The alternatives were considered and rejected:

| Option | Effort | Long-term cost | Decision |
| --- | --- | --- | --- |
| Fork: maintain ULP-IN and ULP-US as separate codebases | Medium short-term | High (2x maintenance forever) | Rejected |
| Wrap: keep ULP-IN, add US as a wrapper layer | Low short-term | High (technical debt accumulates) | Rejected |
| Refactor: redesign as multi-region platform with country compliance plugins | Higher short-term | Low (each new country becomes a plugin) | Selected |
| Rebuild: throw away ULP-IN, build US-first platform | Very high | Loses 5 months of investment | Rejected |

## 2.2 Architectural pattern

Country-specific concerns are extracted into compliance plugins behind shared interfaces:

- Core platform (country-agnostic): Auth, RBAC, multi-tenancy, master data, document management, dashboards, notifications, accounting GL primitives, WMS, transportation operations

- India compliance plugin: ICEGATE filing, GST IRN, e-Way Bill, SCMTR, DGFT schemes, TDS/TCS, GSTR returns, Indian permits/POAs

- US compliance plugin: CBP/ABI filing, AES export, ATM/ITN, 7501 entry summary, PGA holds, US sales tax (state-by-state), 1099 reporting, GAAP period close

At runtime, the tenant configuration determines which compliance plugin loads. A US tenant sees ATM/ITN/Letter of Guarantee; an India tenant sees BOE/SB/EWB. Some tenants (multi-region operators) may load both.

# 3. Complete Document List (21 docs)

All 21 documents — both reworked and new. Status as of project rework start.

### 3.1 Foundation Tier (must complete first — 4 docs)

These four documents are the foundation. They MUST be completed first because all other documents reference them. They unlock the client conversation and provide the architectural baseline for everything else.

| # | Document | Status | Priority | Hours |
| --- | --- | --- | --- | --- |
| F1 | ULP_Rework_MasterPlan_v1.0.docx | NEW | P0 | 8 |
| F2 | ULP_Internationalization_Guide_v1.0.docx | NEW | P0 | 8 |
| F3 | ULP_HLD_v2.0_MultiRegion.docx | REWORK (60p, 30%) | P0 | 18 |
| F4 | ULP_DevelopmentSequencing_v2.0.docx | REWORK (21p, 50%) | P0 | 10 |

### 3.2 Tier 1: US-Specific New Documents (next - 2 docs)

After foundation, these two new documents address the largest US compliance gaps. Without these, the client cannot evaluate the platform for US operations.

| # | Document | Status | Priority | Hours |
| --- | --- | --- | --- | --- |
| T1.1 | ULP_LLD_M4_US_CBP_ABI_v1.0.docx (~40p) | NEW | P1 | 22 |
| T1.2 | ULP_LLD_M17_US_Accounts_GAAP_v1.0.docx (~30p) | NEW | P1 | 16 |

### 3.3 Tier 2: Major Rework (4 docs, >40% rework)

| # | Document | Original | Rework | Hours |
| --- | --- | --- | --- | --- |
| T2.1 | ULP_LLD_M4_CHA.docx | 45p | 70% | 30 |
| T2.2 | ULP_LLD_M17_Accounts.docx | 58p | 50% | 28 |
| T2.3 | ULP_DomainReferenceLibrary_v3.0.docx | 20p | 40% | 10 |
| T2.4 | ULP_LLD_M13_Transportation.docx | 47p | 30% | 14 |

### 3.4 Tier 3: Moderate Rework (7 docs, 15-30% rework)

| # | Document | Original | Rework | Hours |
| --- | --- | --- | --- | --- |
| T3.1 | ULP_DBD_v1.0_DatabaseDesign.docx | 84p | 15% | 14 |
| T3.2 | ULP_DBD_v1.0_Schema.sql | 981 lines | 15% | 6 |
| T3.3 | ULP_LLD_M1_MasterData.docx | 49p | 25% | 12 |
| T3.4 | ULP_LLD_M24_Dashboards.docx | 51p | 15% | 8 |
| T3.5 | ULP_ArchitectureDecisionMatrix_v3.0.xlsx | 7 sheets | 25% | 6 |
| T3.6 | ULP_DevelopmentGuide_v1.0.docx | 23p | 15% | 5 |
| T3.7 | ULP_ReviewChecklists_v1.0.xlsx | 10 sheets | 20% | 6 |

### 3.5 Tier 4: Minor Rework (4 docs, <15% rework)

| # | Document | Original | Rework | Hours |
| --- | --- | --- | --- | --- |
| T4.1 | ULP_TechStack_v3.0_Final.xlsx | 16 sheets | 10% | 4 |
| T4.2 | ULP_LLD_M8_WMS.docx | 48p | 5% | 3 |
| T4.3 | ULP_DBD_v1.0_TableCatalog.xlsx | - | 15% | 3 |
| T4.4 | ULP_DomainReferenceLibrary_v3.0_MasterCatalog.csv | 1409 rows | 15% | 5 |

Grand total: 21 documents, ~225 hours of writing/rework effort.

# 4. Delivery Roadmap

The 21 documents are delivered in 5 waves. Each wave is sequenced to maximize client value and minimize rework cycles.

## 4.1 Wave 1: Foundation (this session)

Goal: establish multi-region architecture and unblock the client conversation.

- F1: Master Plan (you are reading it)

- F2: Internationalization Guide (the foundation reference doc)

- F3: HLD v2.0 (multi-region architecture)

- F4: Development Sequencing v2.0 (international timeline)

Outcome: Client gets a complete picture of how ULP will serve them in 6 weeks. Foundation for all subsequent work locked.

## 4.2 Wave 2: US-Specific New LLDs

Goal: prove US technical depth to client.

- T1.1: M4-US CBP/ABI LLD (CBP customs filing, ABI/AES, ATM, ITN, 7501)

- T1.2: M17-US GAAP LLD (US accounting, sales tax, 1099 reporting)

Outcome: Client signs off on US-specific compliance design. Engineering can scope these modules independently.

## 4.3 Wave 3: Major Rework

Goal: align existing core modules with multi-region pattern.

- T2.1: M4 CHA refactored to be India-plugin (depends on Wave 2)

- T2.2: M17 Accounts refactored to be India-plugin

- T2.3: Domain Reference Library expanded for US logistics terminology

- T2.4: M13 Transportation refactored (US trucking compliance: DOT, ELD, IFTA)

## 4.4 Wave 4: Moderate Rework

Goal: complete the architectural refactor across remaining core artifacts.

- T3.1-T3.7: DBD, Schema SQL, M1, M24, ADM, Dev Guide, Review Checklists

## 4.5 Wave 5: Minor Touch-up

Goal: cleanup and consistency.

- T4.1-T4.4: TechStack, M8 WMS, Table Catalog, Master Catalog CSV

### 4.6 Wave durations

| Wave | Documents | Hours | Calendar (full-time) | Calendar (evenings) |
| --- | --- | --- | --- | --- |
| Wave 1 | 4 | 44 | 5-6 days | 14-16 days |
| Wave 2 | 2 | 38 | 5 days | 12-14 days |
| Wave 3 | 4 | 82 | 10-11 days | 27-30 days |
| Wave 4 | 7 | 57 | 7-8 days | 19-21 days |
| Wave 5 | 4 | 15 | 2 days | 5-6 days |
| TOTAL | 21 | 236 | 29-32 days | 77-87 days |

# 5. What Changes in Each Document

Specific change descriptions per document. Use this as the change-log target when reworking each document.

## 5.1 Foundation Tier

#### F1: Master Plan

- NEW document. Captures rework strategy, document list, roadmap, and metrics. Updated as the rework progresses.

#### F2: Internationalization Guide

- NEW document. Defines region/country/locale model, currency abstraction, time zone handling, address formats, tax/compliance plugin pattern, language pack structure, deployment per region.

#### F3: HLD v2.0

- Add Section 1.4 Multi-Region Strategy with India + US first, expansion path for future

- Refactor Section 4 Architecture to introduce Compliance Plugin Pattern

- Refactor Section 6 Deployment Topology to show India region (Central India + East US 2 DR) and US region (East US 2 + West US 2 DR), independent stacks per region

- Add Section 7.X Currency, Tax, Locale Services as cross-cutting concerns

- Update Section 9 Module Catalog: split country-specific modules into M4-IN/M4-US, M17-IN/M17-US, etc.

#### F4: Development Sequencing v2.0

- Reorder phases to deliver country-agnostic core first, then country plugins

- Phase 1 (months 1-3): Core platform (M1, M21, M26, M27, M3, M14)

- Phase 2 (months 4-5): Operations (M4-core, M5, M8, M13-core, M17-core/GL primitives)

- Phase 3 (months 6-7): India compliance plugins (M4-IN, M13-IN/EWB, M17-IN/GST/TDS)

- Phase 4 (months 6-7 parallel): US compliance plugins (M4-US/CBP, M17-US/GAAP, M13-US/DOT)

- Phase 5 (months 8-9): Dashboards (M24), reports, polish, hardening

- Reorder maps directly onto the client 6-milestone proposal

## 5.2 Tier 1: US-Specific New LLDs

#### T1.1: M4-US CBP/ABI LLD

- CBP ACE (Automated Commercial Environment) integration

- ABI (Automated Broker Interface) message types: SE, SO, etc.

- AES (Automated Export System) for export filing

- CBP Form 7501 entry summary structure and computation

- Authority to Make Entry (ATM) and Immediate Transportation (I.T.) workflows

- PGA (Partner Government Agency) holds: FDA, USDA, EPA, FCC integration

- US Customs Hold/Exam Notice handling

- Letter of Guarantee, Delivery Order, Release Instructions, Turnover/Release Order doc generation

- FIRMS Code (Facility Identification) lookup integration

- ISF (Importer Security Filing / 10+2)

#### T1.2: M17-US GAAP LLD

- US GAAP period close (vs Indian Ind AS)

- US sales tax: state-by-state computation, nexus rules, marketplace facilitator rules

- 1099 reporting (1099-NEC, 1099-MISC, 1099-K) and W-9 vendor onboarding

- Form 1040 / Form 1120 reporting hooks

- US bank reconciliation conventions

- US-specific document templates: AR Invoice, AP Invoice, Statement of Account, etc.

- No TDS/TCS, no GSTR returns; replaced with W-9, 1099, sales tax filing

## 5.3 Tier 2: Major Rework

#### T2.1: M4 CHA refactor

- Extract module into M4-Core (universal: shipment lifecycle, MBL/HBL, document management) + M4-IN-Plugin (ICEGATE/SCMTR-specific) + M4-US-Plugin (CBP/ABI-specific)

- Update all references to point to plugin pattern

- M4-Core code that already exists is mostly reusable; just relocated

#### T2.2: M17 Accounts refactor

- Extract M17-Core (GL, AR, AP, ageing, dunning, period-close-primitives, audit trail) + M17-IN-Plugin (GST/IRN/TDS) + M17-US-Plugin (sales tax/1099/GAAP)

- Currency abstraction made first-class (functional currency per tenant)

- Multi-currency journals with FX revaluation

#### T2.3: Domain Reference Library expansion

- Section 4 Customs domain: add US CBP/ABI/AES/ATM/ITN/7501/PGA terminology

- Section 5 Accounts domain: add US GAAP/sales tax/1099/W-9 terminology

- Section 6 Transportation domain: add US DOT/ELD/IFTA/HOS terminology

- New Section 12: Internationalization terminology (locale, region, currency, time zone)

#### T2.4: M13 Transportation refactor

- Extract M13-Core (trip lifecycle, GPS, geofencing, POD) + M13-IN-Plugin (e-Way Bill) + M13-US-Plugin (DOT, ELD mandate, IFTA, HOS)

- Driver app: support both Indian and US driver licensing rules

- Distance: km vs miles toggle

## 5.4 Tier 3 + 4: Quick reference

- All other docs: add country_code field where compliance applies, swap "tenant_id" examples to "tenant_id + country_code", add multi-region examples

- Mostly mechanical updates; bulk of effort in this tier is on M1 (master data: address formats, identifiers, permits per country)

# 6. Risks and Mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Scope creep — client requests additional regions during refactor | Medium | High | Cap rework at India + US for v2.0; defer additional regions to v2.1; set clear "extension pattern" in Internationalization Guide so future regions are plug-ins not refactors |
| Architectural drift — different developers interpret plugin pattern differently | High | High | Internationalization Guide (F2) is the single source of truth; mandatory for all new module work |
| Documentation debt — code outpaces doc updates | High | Medium | Wave-by-wave delivery; only start Wave N+1 after Wave N docs are signed off |
| Indian client rejects deferred features — sees parallel US work as deprioritization | Medium | High | Communicate clearly: India work continues uninterrupted in Phase 3; US work is parallel in Phase 4; both deliver simultaneously |
| US client rejects Indian-influenced design choices | Medium | Medium | Internationalization Guide makes everything country-pluggable; demonstrate with US-specific demos |
| Database design needs deeper rework than estimated | Low | High | Multi-tenancy already mandates tenant_id; adding country_code is a small extension; if deeper changes needed, escalate to Wave 0 (additional foundation) |
| Existing investment in 32 Claude Code skills bundle becomes obsolete | Low | Low | Skills bundle is country-agnostic for ~24 of 32; only 8 logistics-domain skills need US variants — to be added as Wave 2 deliverable |

# 7. Success Criteria

Each wave has explicit acceptance criteria. The rework is complete when all criteria are met across all 5 waves.

## 7.1 Wave 1 acceptance (Foundation)

- Multi-region strategy ratified by both clients (Indian and US)

- Internationalization Guide approved by tech lead

- HLD v2.0 walked through with engineering team without major architectural objections

- Development Sequencing v2.0 produces a credible 9-month timeline aligned to client milestones

## 7.2 Wave 2 acceptance (US LLDs)

- M4-US LLD reviewed by US customs broker SME (external if needed)

- M17-US LLD reviewed by US CPA or accountant SME

- Engineering can produce a t-shirt-sized estimate (S/M/L/XL) per LLD section

## 7.3 Wave 3-5 acceptance

- All 21 documents sign-off complete by ULP project owner

- Engineering can produce sprint-level estimates per module

- Both Indian and US clients receive their respective tailored deliverable docs

- All cross-references between documents resolve correctly

- Document version numbers and dates updated consistently

# 8. Appendix: Per-Document Change Log Template

Each reworked document MUST have a change log section added. Use this template:

## Change Log

| Version | Date       | Author   | Changes |

|---------|------------|----------|---------|

| 1.0     | 2026-04-26 | Shankar  | Initial release (India-only) |

| 2.0     | 2026-05-XX | Shankar  | Multi-region refactor: India + US support |

|         |            |          | - Added country_code on tenant + table layer |

|         |            |          | - Refactored module M4 into Core + IN-plugin + US-plugin |

|         |            |          | - New Section X.Y on US-specific patterns |

Change logs must be present at the END of every document for traceability.

## 8.1 Document version policy

- Major (X.0): structural changes, new compliance regime, breaking schema changes

- Minor (X.Y): content additions, clarifications, non-breaking schema additions

- Patch (X.Y.Z): typo fixes, clarifications, broken-link fixes

Current rework target: all v1.x documents become v2.0.

— End of Master Plan —